## Datasheet (hidden)
What is the source of data here? IPTS?
Note: Source data IPTS
| Dependant Variable (Y) | Independent Variables (X1, X2, X3, X4…)
| Forecast Variable | Assumption 1 | Assumption 2 | Assumption 3
Module name | Defect Rate | Code Creation Effort | Code Review Effort | Code Rework Effort
7.3.1 - Dncc Control Phase-2 Part1 | 2 | 305 | 3.5 | 2.2
7.4.0 - Web1.5 | 3.2 | 130 | 2.5 | 2
Jupiter - 1.5 | 8 | 213 | 1.5 | 2.5
Rel 2.0 | 1.4915 | 436.25 | 14.75 | 145.25
TAF 8.6.1 | 0.70833 | 184 | 24 | 121

## Readme (hidden)
Quantitative Pro
Read me: In Process
Points to verify in Regression Equation
1) P value < 0.05
2) R square (adj) > 80%
3) VIF should be between 0 and 5 (Maximum can be 10)
Steps for PPM Execution
1) Ensure "Simulcion" is installed. Contact QG POC for details. Do not write anything in Section I
2) Fill Section II a. Select threshold value to monitor probability of success. Reference range: 60%-80%
3) Mention the USL and LSL for the PPM
4) Run Simulacion. <Click "Run Simulation" button on "Add-Ins">
5) Fill Section II b with the help Summary tab in excel sheet resulted after running simulations
6) Fill Section III with the help Sensitivity tab in excel sheet resulted after running simulations
7) Fill Section V if required. Check Result from Section IV.
8) Fill POS in Section VI under Planning using POS value from Section IV. Fill Estimated under Section VII using Mean (Y) under Section II b
9) Section VI needs to be filled during execution with actuals.
<Source of actuals is IPTS>
10) After completion of each phase POS is calculated again and documented in Section VI
11) Replace actual value of the completed phase under assumptions in Section I. Don't overwrite Forecast.
12) Re run simulations and repeat step 5. Verify Result in Section IV for What If Analysis
13) Update Section VI with actual value of completed phase (parameter) and POS
14) Repeat Step 9 onwards untill all phases are completed
15) Fill Section VII once all phases are executed and Y is calculated with actual value.
Points to be addressed
When to trigger CAR?
SPC of Critical Sub-process
Read me document

## 子过程选择
QPPO目标 | 降低遗留缺陷密度 | 目的 | 选择影响QPPO目标的子过程
决策日期 | 2022-01-06 | 决策人员 | 俞凯杰、王正宁、许逸飞、王松、黄利娜、徐嘉颖
子过程 | 目标相关性 | 数据充足度 | 过程可控性 | 生命周期阶段 | 总计 | 选择结果
需求调研 | 1 | 3 | 3 | 5 | 12 | ◎
需求编写 | 1 | 1 | 3 | 5 | 10 | ◎
需求评审 | 5 | 5 | 5 | 2 | 17 | ●
设计文档编写 | 1 | 3 | 3 | 4 | 11 | ◎
设计评审 | 5 | 5 | 5 | 4 | 19 | ●
编码 | 5 | 3 | 3 | 3 | 14 | ◎
代码走查 | 5 | 5 | 5 | 3 | 18 | ●
单元测试 | 1 | 5 | 3 | 3 | 12 | ◎
集成测试 | 3 | 3 | 3 | 2 | 11 | ◎
系统测试 | 5 | 5 | 5 | 2 | 17 | ●
验收测试 | 4 | 5 | 5 | 4 | 18 | ●
1代表不相关
2代表微相关
3代表相关
4代表较相关
5代表强相关
选择结果需总分15以上

## 子过程度量项选择
QPPO目标 | 降低遗留缺陷密度 | 目的 | 选择影响QPPO目标的子过程度量项
决策日期 | 2022-01-10 | 决策人员 | 俞凯杰、王正宁、许逸飞、王松、黄利娜、徐嘉颖
子过程 | 子过程度量项 （Metrics) | 目标相关性 | 历史数据可用性 | 数据充足度 | 改进成本 | 可操作性 | 总计 | 选择结果
需求 | 工作量 | 3 | 3 | 4 | 1 | 3 | 14 | ◎
| 生产率 | 5 | 5 | 5 | 5 | 1 | 21 | ●
| 缺陷密度 | 5 | 5 | 5 | 5 | 5 | 25 | ●
设计 | 工作量 | 2 | 5 | 3 | 1 | 3 | 14 | ◎
| 生产率 | 5 | 5 | 5 | 5 | 1 | 21 | ●
| 缺陷密度 | 5 | 5 | 5 | 5 | 5 | 25 | ●
编码 | 工作量 | 2 | 5 | 3 | 1 | 3 | 14 | ◎
| 生产率 | 5 | 5 | 5 | 5 | 1 | 21 | ●
| 缺陷密度 | 5 | 5 | 5 | 5 | 5 | 25 | ●
系统测试 | 工作量 | 5 | 2 | 3 | 1 | 2 | 13 | ◎
| 生产率 | 5 | 2 | 2 | 2 | 1 | 12 | ◎
| 缺陷密度 | 5 | 5 | 5 | 5 | 5 | 25 | ●
验收测试 | 工作量 | 2 | 2 | 2 | 1 | 5 | 12 | ◎
| 生产率 | 2 | 2 | 2 | 5 | 1 | 12 | ◎
| 缺陷密度 | 5 | 5 | 5 | 5 | 5 | 25 | ●
1代表不相关
2代表微相关
3代表相关
4代表较相关
5代表强相关
选择结果需总分15以上

## 子过程度量项定义
子过程 | 子过程度量项 | 计算公式
需求评审 | 需求评审缺陷密度 | 需求评审发现的缺陷数/评审文档的页数
设计评审 | 设计评审缺陷密度 | 设计评审发现的缺陷数 / 评审文档的页数
代码走查 | 代码走查缺陷密度 | 代码走查发现的缺陷数/项目估算功能点数
系统测试 | 系统测试缺陷密度 | 系统测试发现缺陷数量/功能点数